## Sheet1
Date	Task	Priority	Description	Status	Comment
24.3.2022	Misc	1	Move record to Manjaro	+

27.2.2022	Patterns	4	Aggregate patterns
27.2.2022	Patterns	4	Lightweight
27.2.2022	Patterns	4	Proxy
27.2.2022	Patterns	4	Facade
27.2.2022	Patterns	4	…

21.3.2022	Protocols	2	Add doc	+

21.3.2022	UML	1	UML for Manjaro!	+

24.3.2022	TestSys	1	Design
24.3.2022	UML	1	Draw UML	+
26.3.2022	Protocols	1	Safeguard from collisions	+
26.3.2022	Protocols	1	Give each protocol a universal dir in tmp	-
26.3.2022	Protocols	1	Randomize decrease step	+
24.3.2022	Protocols	1	Switch to UserSubmittedData!	+
24.3.2022	Submissions	1	Implement UserSubmittedData class	+
24.3.2022	Protocols	1	Check return type: str → Verdict	+
24.3.2022	Submissions	1	Implement Verdict class	+
24.3.2022	Submissions	1	Implement ExtendedSubmissionData class	+
24.3.2022	Problems	1	Implement ProblemData class	+
25.3.2022	Protocols	1	Store opts with protocols	+
25.3.2022	Problems	1	Language support
26.3.2022	Protocols	1	Bring convert_to_executable_fun out of TestingProtocol class	+
26.3.2022	Protocols	1	conversion ret type: Path → int – to trace CE	+
27.3.2022	Protocols	1	InOut: truncate newlines	+
27.3.2022	Protocols	1	Truncate correct output on initialization?	+
27.3.2022	Protocols	1	InCustom: get_custom_checker_verdict	+
27.3.2022	Protocols	1	Support RE!	+
27.3.2022	Protocols	1	Organize sample_tests dir

24.3.2022	Deadline (27.3.2022)	1	Review1
28.3.2022	Py	1	Write README	+
24.3.2022	Py	3	Fix import	?
24.3.2022	Py	1	Main part
24.3.2022	Py	1	1. Supported languages:
24.3.2022	Py	1	1.1 C++	+
	Py	1	tests	+
24.3.2022	Py	1	1.2 Java/Scala
	Py	1	tests
24.3.2022	Py	1	1.3 Python	+
	Py	1	tests	+
24.3.2022	Py	1	1.4 Haskell	+!
	Py	1	tests
24.3.2022	Py	1	2. Supported protocols:	+
24.3.2022	Py	1	2.1 InOut	+
24.3.2022	Py	1	2.2 InCustomChecker	+
24.3.2022	Py	1	2.3 RandIntCustomChecker	+
24.3.2022	Py	1	2.4 LimitedWorkSpace	+
24.3.2022	Py	3	Bonus part
24.3.2022	Py	3	3. Style checker support
24.3.2022	Py	3	4. Valgrind support
24.3.2022	Py	3	5. Resource safety
24.3.2022	Py	3	6. Keep track of error types