## Sheet1
Date	Task	Priority	Description	Status	Comment
24.3.2022	Misc	1	Move record to Manjaro	+

27.2.2022	Patterns	4	Aggregate patterns
9.4.2022	Patterns	2	Singleton
9.4.2022	Patterns	2	Borg		https://stackoverflow.com/a/6255101/11143763 / https://code.activestate.com/recipes/66531-singleton-we-dont-need-no-stinkin-singleton-the-bo/
9.4.2022	Patterns	2	Factory
27.2.2022	Patterns	4	Lightweight
27.2.2022	Patterns	4	Proxy
27.2.2022	Patterns	4	Facade
27.2.2022	Patterns	4	…

21.3.2022	Protocols	2	Add doc	+

21.3.2022	UML	1	UML for Manjaro!	+

24.3.2022	TestSys	1	Design	+
24.3.2022	UML	1	Draw UML	+
26.3.2022	Protocols	1	Safeguard from collisions	+
26.3.2022	Protocols	1	Give each protocol a universal dir in tmp	-
26.3.2022	Protocols	1	Randomize decrease step	+
24.3.2022	Protocols	1	Switch to UserSubmittedData!	+
24.3.2022	Submissions	1	Implement UserSubmittedData class	+
24.3.2022	Protocols	1	Check return type: str → Verdict	+
24.3.2022	Submissions	1	Implement Verdict class	+
24.3.2022	Submissions	1	Implement ExtendedSubmissionData class	+
24.3.2022	Problems	1	Implement ProblemData class	+
25.3.2022	Protocols	1	Store opts with protocols	+
25.3.2022	Problems	1	Language support	+
26.3.2022	Protocols	1	Bring convert_to_executable_fun out of TestingProtocol class	+
26.3.2022	Protocols	1	conversion ret type: Path → int – to trace CE	+
27.3.2022	Protocols	1	InOut: truncate newlines	+
27.3.2022	Protocols	1	Truncate correct output on initialization?	+
27.3.2022	Protocols	1	InCustom: get_custom_checker_verdict	+
27.3.2022	Protocols	1	Support RE!	+
27.3.2022	Protocols	1	Organize sample_tests dir	-

24.3.2022	Deadline (10.4.2022)	1	Review1
5.4.2022	Py	2	Suppress unwanted stderr in tests	?	SetUp-tearDown?
28.3.2022	Py	1	Write README	+
24.3.2022	Py	1	Fix import	+
5.4.2022	Py	1	Switch to enumerate in test iteration	+
24.3.2022	Py	1	Main part
24.3.2022	Py	1	1. Supported languages:
24.3.2022	Py	1	1.1 C++	+
	Py	1	tests	+
24.3.2022	Py	1	1.2 Java/Scala
	Py	1	tests
24.3.2022	Py	1	1.3 Python	+
	Py	1	tests	+
24.3.2022	Py	1	1.4 Haskell	+!
	Py	1	tests
24.3.2022	Py	1	2. Supported protocols:	+
24.3.2022	Py	1	2.1 InOut	+
24.3.2022	Py	1	2.2 InCustomChecker	+
24.3.2022	Py	1	2.3 RandIntCustomChecker	+
24.3.2022	Py	1	2.4 LimitedWorkSpace	+
24.3.2022	Py	3	Bonus part
24.3.2022	Py	3	3. Style checker support
24.3.2022	Py	3	4. Valgrind support
24.3.2022	Py	3	5. Resource safety
24.3.2022	Py	3	6. Keep track of error types

5.4.2022	TestSys	1	Get rid of:
5.4.2022	TestSys	1	Copy&paste in tests	+
5.4.2022	TestSys	1	Junk	?

28.3.2022	Misc	1	Create alias for cd to project dir	!
28.3.2022	Misc	1	Automatically rerender diagrams	!

5.4.2022	Deadline (10.4.2022)	1	Review1+Checkpoint2		https://docs.google.com/document/d/11DyYqOErt1Lqi2cNr0uTCBUOfDZnr5vNbpcjpfjyZBc/edit
5.4.2022	IF	1	Design IF-TestingSystem interaction protocol
5.4.2022	Cmd	1	Design
5.4.2022	Cmd	1	Problem upload
9.4.2022	Cmd	1	UseCase	+-
9.4.2022	Cmd	1	Incorrect <<include>> use?
9.4.2022	Cmd	1	Activity	+
9.4.2022	Cmd	1	Class
5.4.2022	Cmd	1	Submission upload
9.4.2022	Web	3	Choose statement file format
9.4.2022	Web	3	PDF?		https://stackoverflow.com/questions/17784037/how-to-display-pdf-file-in-html

9.4.2022	Protocols	3	Rename diagram to Class_TestingProtocols